## Read Me
BookMyShow Clone — Microservices Requirements
Prepared as a developer-facing spec. 10-day build target. React frontend is already built with dummy data (see the accompanying frontend zip) — this doc is the contract your services must satisfy.
Sheet | What's in it
Build Order | Day-by-day (10 days) plan: what to build, in what order, and why that order avoids rework.
Microservices | Every service, its single responsibility, DB, port, and what it depends on.
Endpoints | Every REST endpoint: method, path, request body, response body, auth, sync/async, resilience notes.
Communication Matrix | Which service calls which, sync vs async, protocol, and what happens on failure.
Concepts Checklist | The non-functional concepts (retry, circuit breaker, saga, logging, testing...) mapped to exactly where you'll implement each one.
Tech Stack | Current, non-deprecated libraries/tools to use for each part of the system (green = use this, red = avoid/deprecated), with the reasoning.
Learn Before You Start | Prerequisite concepts ordered by priority — what to shore up before Day 1 vs what to learn just-in-time on the day it's needed.
Every Status cell is a dropdown (Not Started / In Progress / Blocked / Done). Update as you build — this is your single source of truth for progress.

## Build Order
Day | Focus | Microservice(s) | Tasks | Concepts You Practice | Status
1 | Foundations | Discovery Server, API Gateway, Config Server | Spring Cloud Eureka up; Gateway routes /api/** stubs to nothing yet; externalize config; docker-compose skeleton with Postgres + pgAdmin. | Service discovery, API Gateway routing, config externalization, Docker Compose
2 | User Service | User Service | Register/Login endpoints; JWT issuance; password hashing (BCrypt); register with Eureka; route through Gateway. | Spring Security, JWT, password hashing, service registration
3 | Catalog Service | Movie/Catalog Service | CRUD for movies; seed data; GET /api/movies and /api/movies/{id}; unit tests for service layer. | REST API design, JPA basics, JUnit + Mockito unit testing
4 | Theatre/Show Service (part 1) | Theatre Service | Theatre, Screen, Show entities; GET /api/shows?movieId=; seat layout generation and GET /api/shows/{id}/seats. | Relational modeling (1:N, N:N), DTO mapping
5 | Theatre/Show Service (part 2) — concurrency | Theatre Service | POST /api/shows/{id}/seats/lock with short-lived lock (DB row lock or Redis TTL key); handle two users racing for the same seat. | Optimistic vs pessimistic locking, @Version, race conditions
6 | Booking Service — the Saga | Booking Service, Theatre Service, Payment Service | POST /api/bookings creates booking in PENDING; sync call to Payment Service; on success mark CONFIRMED, on failure release seats (compensating transaction). | Saga pattern (orchestration-based), distributed transactions, compensating transactions, RestClient/OpenFeign
7 | Payment Service + Async Messaging | Payment Service, Notification Service, Kafka/RabbitMQ | Mock payment gateway (random success/fail); publish BookingConfirmed event; Notification Service consumes it and 'sends' an email (log it). | Async messaging, event-driven architecture, pub/sub, idempotent consumers
8 | Resilience | Booking Service, Theatre Service, Payment Service | Wrap inter-service sync calls with Resilience4j: Circuit Breaker on Payment calls, Retry with backoff on transient failures, fallback methods, timeouts. | Circuit breaker, retry with exponential backoff, bulkhead, timeout, fallback design
9 | Observability + Testing | All services | Centralized logging (ELK or just structured JSON logs + correlation ID via Sleuth/Micrometer Tracing + Zipkin); integration tests with Testcontainers; contract tests for critical endpoints. | Centralized logging, distributed tracing, correlation IDs, integration testing, Testcontainers
10 | Frontend Integration + Polish | All services + React frontend | Flip USE_DUMMY_DATA=false in frontend; wire real Gateway URL; smoke-test full flow: browse -> book -> pay -> view booking; write README; docker-compose up end-to-end. | End-to-end integration, environment configuration, demo readiness

## Microservices
Microservice | Single Responsibility | Port | Database | Depends On (Sync) | Depends On (Async) | Status
Discovery Server (Eureka) | Service registry — every other service registers here on startup. | 8761 | - | - | -
API Gateway | Single entry point for the frontend; routes /api/** to the right service; can also do auth token validation at the edge. | 8080 | - | All services (routing only) | -
Config Server | Centralized externalized config for all services (optional but recommended for the resilience/retry configs in Day 8). | 8888 | - | - | -
User Service | Registration, login, JWT issuance, user profile. | 8081 | user_db (Postgres) | - | -
Catalog Service | Movie metadata: title, genre, language, cast, rating. | 8082 | catalog_db (Postgres) | - | -
Theatre Service | Theatres, screens, shows/showtimes, seat layout and seat locking. | 8083 | theatre_db (Postgres) | Catalog Service (validate movieId) | -
Booking Service | Owns the booking lifecycle end to end; orchestrates the saga. | 8084 | booking_db (Postgres) | Theatre Service (lock/confirm seats), Payment Service (charge) | Publishes BookingConfirmed / BookingFailed
Payment Service | Mock payment processing; owns payment status. | 8085 | payment_db (Postgres) | - | Publishes PaymentSucceeded / PaymentFailed
Notification Service | Sends (mock) email/SMS on booking confirmation. | 8086 | - (stateless, or a small log table) | - | Consumes BookingConfirmed

## Endpoints
Microservice | Method | Path | Description | Request Body | Response Body (200) | Auth Required | Sync/Async | Resilience Notes | Status
User Service | POST | /api/auth/register | Create a new account. | { "name": string, "email": string, "password": string } | { "userId": string, "name": string, "email": string } | No | Sync (REST) | Validate uniqueness of email; hash password before persisting.
User Service | POST | /api/auth/login | Authenticate and issue a JWT. | { "email": string, "password": string } | { "token": string, "user": { "userId": string, "name": string, "email": string } } | No | Sync (REST) | Rate-limit login attempts (bonus). Return 401 on bad credentials, never leak which field was wrong.
User Service | GET | /api/users/{userId} | Fetch a user profile. | - | { "userId": string, "name": string, "email": string } | Yes (JWT) | Sync (REST) | -
Catalog Service | GET | /api/movies | List all movies currently showing. | - | [ { "movieId": string, "title": string, "language": string, "genre": string[], "durationMins": number, "rating": number, "posterUrl": string, "description": string } ] | No | Sync (REST) | Cache this response (rarely changes) — good candidate for @Cacheable / Redis cache.
Catalog Service | GET | /api/movies/{movieId} | Fetch one movie's detail. | - | { "movieId": string, "title": string, ... same shape as above } | No | Sync (REST) | Return 404 if movieId doesn't exist.
Theatre Service | GET | /api/shows?movieId={movieId} | List showtimes for a movie across theatres. | - | [ { "showId": string, "theatreName": string, "screen": string, "time": string, "price": number } ] | No | Sync (REST) | Calls Catalog Service to validate movieId exists (or trust the ID and let it 404 downstream — document your choice).
Theatre Service | GET | /api/shows/{showId}/seats | Get the seat layout with current status. | - | [ { "row": string, "seats": [ { "seatId": string, "status": "AVAILABLE¦BOOKED¦LOCKED", "tier": "PREMIUM¦NORMAL" } ] } ] | Yes (JWT) | Sync (REST) | This is your read path — keep it fast, no locking here, just current state.
Theatre Service | POST | /api/shows/{showId}/seats/lock | Temporarily lock seats while user pays (TTL ~5 min). | { "seatIds": string[], "userId": string } | { "locked": boolean, "lockExpiresInSeconds": number } | Yes (JWT) | Sync (REST) | THE concurrency hotspot. Use @Version optimistic locking or a Redis SETNX key. Return 409 Conflict if any seat is already locked/booked.
Booking Service | POST | /api/bookings | Create a booking and kick off the payment saga. | { "showId": string, "seatIds": string[], "userId": string, "amount": number } | { "bookingId": string, "status": "PAYMENT_PENDING", "paymentId": string, "seats": string[], "amount": number } | Yes (JWT) | Sync + Async | Saga orchestrator. Sync call to Payment Service to initiate charge; on failure, compensating call back to Theatre Service to release seats.
Booking Service | GET | /api/bookings/{bookingId} | Fetch one booking's current state. | - | { "bookingId": string, "status": "PENDING¦CONFIRMED¦FAILED", "seats": string[], "amount": number } | Yes (JWT) | Sync (REST) | -
Booking Service | GET | /api/bookings/user/{userId} | List a user's booking history. | - | [ { "bookingId": string, "movieTitle": string, "theatreName": string, "time": string, "seats": string[], "amount": number, "status": string } ] | Yes (JWT) | Sync (REST) | Consider a read-optimized denormalized view (CQRS) fed by BookingConfirmed events instead of joining across services live.
Payment Service | POST | /api/payments/process (internal) | Charge for a booking. Usually called by Booking Service, not the frontend. | { "bookingId": string, "amount": number, "userId": string } | { "paymentId": string, "status": "SUCCESS¦FAILED" } | Service-to-service (internal token) | Sync (REST) | Wrap the CALLER'S invocation of this in Resilience4j Circuit Breaker + Retry (exponential backoff, max 3 attempts).
Payment Service | GET | /api/payments/{paymentId} | Poll a payment's status (frontend uses this). | - | { "paymentId": string, "status": "PROCESSING¦SUCCESS¦FAILED" } | Yes (JWT) | Sync (REST) | Frontend polls this with backoff; good place to practice client-side retry too.
Notification Service | (consumer only) | Kafka topic: booking.confirmed | Sends a confirmation email/SMS when a booking is confirmed. | Event: { "bookingId": string, "userId": string, "email": string, "movieTitle": string, "time": string } | - (no HTTP response, fire-and-forget) | N/A | Async (Kafka/Event) | Make the consumer idempotent (dedupe by bookingId) — Kafka can redeliver.

## Communication Matrix
Caller | Callee | Type | Protocol | Purpose | On Failure
Frontend | API Gateway | Sync | HTTPS/REST | All user-facing calls | Show error toast; retry button
API Gateway | User / Catalog / Theatre / Booking / Payment | Sync | HTTP (internal) | Route by path prefix | Gateway-level fallback / 503
Theatre Service | Catalog Service | Sync | REST (RestClient/OpenFeign) | Validate movieId when creating a show | Retry x2, then fail the request
Booking Service | Theatre Service | Sync | REST | Lock seats, then confirm/release seats | Circuit breaker; if open, fail booking fast with a clear error
Booking Service | Payment Service | Sync | REST | Initiate charge for a booking | Retry with backoff (max 3), then circuit breaker opens; booking marked FAILED, seats released
Booking Service | Kafka topic booking.confirmed | Async | Kafka (event) | Announce a confirmed booking for downstream consumers | Kafka retains the message; consumer retries on next poll
Notification Service | Kafka topic booking.confirmed | Async | Kafka (event) | Consume event, send confirmation email/SMS | Dead-letter topic after N failed processing attempts
Frontend | Payment Service (via Gateway) | Sync (polling) | REST, polled every 2-3s | Check payment status while user waits | Show 'still processing' state; stop after timeout

## Concepts Checklist
Concept | Where You'll Apply It | Notes / Resource | Status
Synchronous communication (REST) | Gateway -> all services; Theatre -> Catalog; Booking -> Theatre/Payment | Use RestClient or OpenFeign (Spring Cloud) instead of raw RestTemplate.
Asynchronous communication (events) | Booking -> Notification via Kafka/RabbitMQ | Start with RabbitMQ if Kafka feels heavy; concepts transfer either way.
Saga pattern (orchestration) | Booking Service coordinating seat-lock + payment | Booking Service is the orchestrator; each downstream step has a compensating action.
Compensating transactions | Release seats if payment fails | This IS the 'rollback' in a distributed system — there's no real DB rollback across services.
Idempotency | Payment processing, Kafka consumers | Use an idempotency key (bookingId) so a retried request doesn't double-charge.
Optimistic / pessimistic locking | Seat locking in Theatre Service | Try @Version (optimistic) first; compare against SELECT FOR UPDATE (pessimistic).
Circuit Breaker | Booking Service's calls to Payment Service and Theatre Service | Resilience4j @CircuitBreaker; tune failure-rate threshold and open-state wait duration.
Retry with backoff | Booking -> Payment calls; frontend polling Payment status | Resilience4j @Retry; exponential backoff, cap max attempts at 3.
Timeouts | Every inter-service sync call | Never call another service without a timeout — a hung call blocks a thread indefinitely.
Bulkhead | Isolate the thread pool used for Payment calls from the rest of Booking Service | Resilience4j @Bulkhead — prevents one slow dependency from starving the whole service.
Centralized logging | All services | Structured JSON logs + a correlation/trace ID propagated across services (Micrometer Tracing + Zipkin, or the ELK stack).
Distributed tracing | Frontend request -> Gateway -> Booking -> Theatre -> Payment | Zipkin or Jaeger; see one request's full path across 4 services in one trace.
Unit testing | Service layer of every microservice | JUnit 5 + Mockito; mock the repository and downstream clients.
Integration testing | Repository layer, and full request flow per service | Testcontainers spins up a real Postgres/Kafka in Docker for the test run.
Contract testing (bonus) | Booking Service <-> Payment Service | Spring Cloud Contract or Pact — catch breaking API changes before deploy.
Containerization | Every service | One Dockerfile per service (multi-stage build); single docker-compose.yml to run everything.
API Gateway routing | Single entry point for the frontend | Spring Cloud Gateway; route by path prefix; can also centralize JWT validation here.
Service discovery | Every service registers so Gateway/others find it by name, not hardcoded host:port | Netflix Eureka via Spring Cloud Netflix.
Externalized configuration | DB URLs, Kafka brokers, resilience thresholds | Spring Cloud Config Server, or simple per-environment application.yml profiles if short on time.
CQRS (bonus, if time allows) | Booking Service's 'my bookings' read endpoint | Build a denormalized read model updated by consuming your own BookingConfirmed events.

## Tech Stack
Category | Use This | Avoid / Deprecated | Why | Status
Language / Runtime | Java 21 LTS (Java 17 LTS is the floor) | Java 8/11 for new projects | Spring Boot 3.x/4.x require Java 17 minimum. Java 21 LTS is what most production shops target in 2026 — virtual threads, records, pattern matching are all stable there.
Framework | Spring Boot 3.5.x (stable, huge ecosystem) — Spring Boot 4.1.x if you want the newest (needs Java 17+, Spring Framework 7) | Spring Boot 2.x | 3.5 is the safest choice for learning: every tutorial, Stack Overflow answer, and Udemy course still targets 3.x. 4.x is legitimate and current but very new — expect thinner community docs.
Build tool | Maven (or Gradle if you already know it) | - | Either is fine and current; Maven has more copy-pasteable examples for Spring Cloud.
Service registry | Netflix Eureka (via spring-cloud-starter-netflix-eureka-client/server) | - | Still the standard for non-Kubernetes Spring Cloud setups in 2026. (If you later deploy to Kubernetes, K8s' own Service discovery replaces this — good thing to know exists, not needed for a 10-day local build.)
API Gateway | Spring Cloud Gateway (spring-cloud-starter-gateway) | Zuul | Zuul (Netflix) has been deprecated for years. Spring Cloud Gateway is the current standard, actively maintained.
Inter-service sync calls | RestClient (Spring 6.1+) for simple calls, OpenFeign for declarative clients | RestTemplate | RestTemplate has been in maintenance-only mode since Spring 5 and Spring's own docs point people to RestClient/WebClient now. Learn RestClient — it's the modern replacement and still simple to read.
Circuit breaker / retry / bulkhead | Resilience4j (spring-cloud-starter-circuitbreaker-resilience4j) | Netflix Hystrix | Hystrix is officially deprecated/in maintenance mode by Netflix. Resilience4j is the current standard the Spring team recommends, and is what interviewers expect you to name.
Distributed tracing | Micrometer Tracing + Zipkin (or OpenTelemetry + Zipkin/Grafana Tempo) | Spring Cloud Sleuth | Sleuth was merged into / replaced by Micrometer Tracing as of Spring Boot 3. Don't add the old sleuth dependency, it will conflict.
Centralized logging | Structured JSON logs (Logback JSON encoder) shipped to ELK (Elasticsearch+Logstash+Kibana) or Grafana Loki | - | ELK is still an industry staple; Grafana Loki is the lighter-weight, increasingly popular alternative if ELK feels heavy for a 10-day project. Either is a fine, current choice — pick Loki if you want less setup.
Async messaging | Apache Kafka (spring-kafka) for production-grade event streaming, or RabbitMQ (spring-amqp) if you want a gentler learning curve | - | Both are current and widely used in production; Kafka is more common at scale (and more often asked about in interviews), RabbitMQ is faster to get running for a first async project.
Config management | Spring Cloud Config Server, or simple per-profile application.yml if short on time | - | Config Server is the 'proper' production pattern; profile-based yml is a completely acceptable shortcut for a 10-day learning project — just say in your notes which you picked and why.
Database | PostgreSQL (one instance per service, separate schemas/DBs — database-per-service pattern) | - | Postgres is the default production-grade relational choice today; free, well-documented, works great in Docker.
Data access | Spring Data JPA + Hibernate | - | Still the standard. Just be deliberate about N+1 queries and fetch types — a classic interview topic you already have notes on.
Security / Auth | Spring Security 6.x with JWT (jjwt or nimbus-jose-jwt library) | - | Spring Security's newer lambda-based DSL config is current; avoid old WebSecurityConfigurerAdapter-based tutorials (removed since Spring Security 5.7+).
Testing | JUnit 5 (Jupiter) + Mockito + Testcontainers | JUnit 4 | JUnit 5 has been the standard for years now; Testcontainers is the current best practice for integration tests that need a real Postgres/Kafka instance.
Containerization | Docker + Docker Compose (v2, the `docker compose` subcommand, not the old standalone docker-compose binary) | docker-compose v1 (standalone binary) | v1 stopped receiving updates; `docker compose` (space, not hyphen) is bundled with modern Docker Desktop/Engine.
Frontend | React 18/19 with Vite | Create React App (CRA) | CRA was officially deprecated/archived by the React team. Vite is the standard scaffolding tool now — which is what your provided frontend already uses.
API documentation | springdoc-openapi (OpenAPI 3 / Swagger UI) | springfox | Springfox is unmaintained and breaks on newer Spring Boot versions. springdoc-openapi is the actively maintained replacement.

## Learn Before You Start
Priority | Topic | Why You Need It Before Day 1 | Suggested Depth | Status
Must-know (blocking) | Spring Boot fundamentals: REST controllers, @Service/@Repository layering, application.yml profiles | You already have 2+ years on this — this is a refresher, not new learning. | Skim, don't deep-study
Must-know (blocking) | Spring Data JPA basics: entities, relationships, repositories | Every service in this project persists data. If entity relationships (1:N theatre->shows, N:N if any) are shaky, Day 3-4 will stall. | Comfortable writing an entity + repository from scratch, no notes
Must-know (blocking) | Docker + Docker Compose basics | Day 1 sets up the whole skeleton in Docker Compose. If you've never written a docker-compose.yml, do that first — separately, on something small — before Day 1. | Can write a docker-compose.yml with 2-3 services + a Postgres container from memory
Must-know (blocking) | REST API design basics: HTTP verbs, status codes, request/response DTOs vs entities | You'll design ~13 endpoints across 5 services. Sloppy REST design here compounds into every later day. | Comfortable, you likely already have this
Should-know (do on Day 0) | What Eureka / service discovery actually solves | Day 1 wires this up. 30 minutes understanding the client-registers-with-server model before you touch code saves confusion. | Conceptual — 1 short article or video
Should-know (do on Day 0) | What an API Gateway does (and doesn't do) | Also Day 1. Understand routing vs business logic — the Gateway should stay thin. | Conceptual — 1 short article
Should-know (do on Day 0) | JWT structure and how stateless auth works | Day 2 issues and validates JWTs. Know what's IN a JWT (header/payload/signature) before implementing it. | Conceptual, 20-30 mins
Learn just-in-time (Day 4-5) | Optimistic vs pessimistic locking, @Version | Only becomes real once you hit the seat-locking problem on Day 5 — better learned against a concrete bug than in the abstract. | Learn by building; read just before Day 5
Learn just-in-time (Day 6) | Saga pattern (orchestration vs choreography) and compensating transactions | This is new territory for most people at your stage. Spend a focused hour on this the night before Day 6 — it's the conceptual core of the whole project. | 1 focused article/video comparing orchestration vs choreography, pick orchestration for this project
Learn just-in-time (Day 7) | Kafka or RabbitMQ basics: producer/consumer/topic or queue/exchange | You only need enough to publish one event and consume it. Don't over-study Kafka internals (partitions, consumer groups) — that's a rabbit hole outside this project's scope. | Just enough to publish+consume one event; 1-2 hours
Learn just-in-time (Day 8) | Circuit breaker states (closed/open/half-open), retry with exponential backoff | Resilience4j's docs + one example are enough — don't need the theory beyond what makes the demo behave correctly. | Resilience4j 'getting started' guide, 1 hour
Learn just-in-time (Day 9) | What a correlation ID / trace ID is and why logs need one | Makes centralized logging click immediately once you see one request's ID across 3 services' logs. | Conceptual, 20 mins, then just wire it up
Nice-to-have (skip if short on time) | Kubernetes basics (pods, deployments, services) | Not needed for a 10-day local Docker Compose build. Good to know exists for interview conversations, not required to build this project. | Skip for now — revisit after the project is done